## Project Risk Register
Project Risk Register
| Program Name: | Production of Hand Sanitizer and Face Protection Mask
| Executive Sponsor: | Ministry of Health and Safety, Government of Canada |  |  |  |  | Baselined Planned End Date:
| Program Manager: | Senior Manager |  |  |  |  | Version No.: |  | 1
Version Date:
ID | Risk Type | Risk Name | Risk Owner | Risk Description | Current | Current | Risk Response Strategy | Mitigation | Risk Category*
[5 empty] | Likelihood | Impact
Risk Tracking Number | External / Internal Risks | Short name for the risk; ensure it properly describes the risk | Individual or Entity responsible for end-to-end accountability for each listed risk item | Briefly describe the risk and the associated risk triggers; its consequences and any interdependencies impact with target resolution date. | Derived Overall Score | Derived Overall Score | Describe the risk response that will be followed in order to avoid, transfer, mitigate or accept each risk. | Regularly monitor each risk item. Explicitely indicate latest date and status until risk is closed. This is mandatory compliance requirement for internal eHealth Ontario Audit. | Score the likelihood and Impact of each risk for each category on a scale of 1 to 5. Enter 0 in cells for categories that do not apply to a given risk.
[9 empty] | Scope |  | Budget |  | Schedule |  | Technical |  | External/ Internal |  | Contract |  | Adoption
[9 empty] | L | I | L | I | L | I | L | I | L | I | L | I | L | I
R1 | Internal Risk | Production of the Products | Production Manager | Due to the pandemic there is an increased demand of the hand sanitizers and face masks. This makes it difficult for the company to manage the production of the products in a short span of time. | 4 | 5 | Mitigation | Multiple line production processes will be developed and the schedule of the project will be changed. | 3 | 3 | 3 | 4 | 2 | 4 | 3 | 4 | 3 | 2 | 1 | 2 | 0 | 0
R2 | Internal RIsk | Lack of Coordination | Project Manager | As mentioned earlier in the project the team members are new and will be working with each other for the first time and hence, this will affect the work process as the there will be problem in the coordination among the members. | 3 | 4 | Mitigation | A regular team meeting will be arranged and the status of the project will be discussed by the team members. The project manger will be required to manage the coordination by keeping in touch with the head of the different process groups. | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 0 | 0
R3 | Internal Risk | Delay in the deliverables | Project Manager | Due to the pandemic the deadline of the project might be affected as the resources are less and the amount work to be completed is more. | 4 | 4 | Mitigation | The project will be tracked and managed using different project management tools. | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 2 | 3 | 2 | 2 | 0 | 0
R4 | Internal Risk | Lack of resources | Project Manager | The raw material needed for the production of the products are to ordered from other vendors and due to the lockdown the company will face difficulty in getting the resources on time. | 5 | 4 | Mitigation | For the project, more than one vendor would be considered for the supply of raw materials. | 4 | 4 | 4 | 5 | 3 | 4 | 1 | 2 | 3 | 4 | 2 | 3 | 0 | 0
R5 | External Risk | Scarce man force | Human Resource Manager | The contract given by the government is big enough that it requires more workforce and arranging the workforce in such short time is difficult. | 2 | 4 | Transfer | The human resource department is responsible for fulfilling the workforce requirements. | 3 | 4 | 4 | 4 | 2 | 5 | 3 | 4 | 2 | 1 | 3 | 5 | 0 | 0
Overall Program Risk Likelihood & Impact by Category (Maximum category score) | [8 empty] | 4 | 5 | 4 | 5 | 3 | 5 | 3 | 4 | 3 | 4 | 3 | 5 | 0 | 0
Note: Please add new rows for additional Program risks. Please change background color and hide closed risks rows.
Overall Project Risk Results
|  |  |  | Risk Category Item | Probability | Impact | Risk Rating
|  |  |  | Scope | 4 | 5 | Extreme
|  |  |  | Budget | 4 | 5 | Extreme
|  |  |  | Schedule | 3 | 5 | High
|  |  |  | Technical | 3 | 4 | Moderate
|  |  |  | External | 3 | 4 | Moderate
|  |  |  | Contract | 3 | 5 | High
|  |  |  | Adoption | 0 | 0 | Very Low

## Project Risk Map
Risk Map
Program Name: |  | Production of Hand Sanitizer and Face Protection Mask |  |  | Target Program Completion Date: | 1
Program Sponsor: |  | Ministry of Health and Safety, Government of Canada |  |  | Version No.: | 1
Program Manager: |  | Senior Manager |  |  | Version Date:
Risk Map
• After determining and analyzing all potential risks, print out the Risk Register
• Using the risk list, record the ID Number from the risk register in the corresponding square below
Impact | Extreme |  |  |  | R1 Production of the products
| High |  | R5 Scarce Man Force | R2 Lack of Coordination | R3 Delay in the Deliverables | R4 Lack of Resources
Medium
Low
Very Low
|  | Very Low | Low | Medium | High | Extreme
Likelihood
R1
R2
R3
Critical
Risks
(in red)

## Category Table
Risk Category Table*:
A risk may originate from one of following categories.
Category | Description/Examples
Scope | Items to consider: risk of scope increase: project governance issues, project charter issues, work breakdown structure unclear, absence of clinicians in the project team, subject matter decision-making process not in place, poor knowledge of the business sector by the project team, policy failures, scope decision-making process may be delayed, others.
Budget | Items to consider: risk of budget variance, resource requirements, cost estimates identified, cost budget in place, regular project progress reporting against plan not being undertaken, unable to access progress against plan, the risk of financial losses, overspending, or the inability to meet budgets and plans, others
Schedule | Items to consider: risk of schedule slippage or changes, project plan development and execution, change control, lack of experience in projects of the same size, decision-making process may be delayed, deliverables approval process not followed, no detailed plan in place, regular project progress reporting against plan not being undertaken, activity list, activity duration estimates, project schedule and charts, unable to access progress against plan, Other items to consider: is there an integrated deployment plan with all the dependencies between applications aligned and the timelines and interfaces clearly articulated - are the strategies robust enough to withstand organizational restructuring and has that risk been factored in - what about other resource impacting events (e.g flu seasons, employee illness, etc)
Technical | Items to consider: architecture and standards risks, performance risks, solution integration risks, technology risks, operational processes to support business continuity, Information produced or used is incomplete / out-of-date / inaccurate / irrelevant, this initiative will be in breach of a statute / regulation / contract / MOU, others… risks related to the data and information confidentiality, integrity and/ or availability of information as well as any factors resulting in information compromise.
External | Items to consider: risks external to project impact project’s ability to deliver on its commitments. Consider dependence on other data projects, external solutions & services, organizational policies & procedures, pending management approvals or approvals from other external entities, external stakeholders and partners related risks.
Contract | Risks related to compliance with orporate procurement practices, managing vendor procurement and relations, procurement process-related risks.
Adoption | Items to consider: Stakeholder engagement and alignment - do all the job descriptions align with any new roles, changes etc; is there any impact on scope of work within the business units impacted; have all of the impacts been thought through; are staff sufficiently trained and ready; does the proposed information flow alter any current workflow patterns. Are any fundamental business processes going to change/be impacted, do the providers know and are they ready, are the dependencies from a program/business perspective thought through and a solid plan transition plan in place. Client/stakeholder relationships, responsive to client/ stakeholder needs and expectations, client readiness, stakeholder engagement in the program and projects.