## Schedule
ID | Task Name | Effort (days) | Resource (s) | # Resources | Duration (months) | Anticipated Start | Anticipated End | Estimated Costs | Vendor Costs
1 | PLANNING | 106 | Project Manager | 1 | 2.5 | 2011-01-01 | 2011-03-15 | 43160
1.1 | PROJECT ADMINISTRATION | 20 | Project Manager | 1 | 0.90909 | 2011-01-05 | 2011-02-01 | 8450
1.1.1 | Integrated Project Plan | 20 | Project Manager | 1 | 0.90909 | 2011-01-05 | 2011-02-01 | 8450
1.2 | PROCUREMENT | 82 | Project Manager | 1 | 2 | 2011-01-05 | 2011-03-05 | 32955
1.2.1 | Development Team | 30 | Project Manager | 1 | 1.3636 | 2011-01-05 | 2011-02-05 | 12675
1.2.2 | Consultant: Business Analyst & BI Specialist | 48 | Project Manager | 1 | 2.1818 | 2011-01-05 | 2011-03-05 | 20280
1.3 | VENDOR RAMP UP | 4 | SD, Vendor, QA | 3 | 0.060606 | 2011-03-05 | 2011-03-08 | 1755
1.3.1 | I&IT Standards Review Workshop(s) | 2 | SD | 1 | 0.090909 | 2011-03-05 | 2011-03-07 | 845
1.3.2 | I&IT Design & Build Standards Workshop | 1 | SD | 1 | 0.045455 | 2011-03-07 | 2011-03-07 | 422.5
1.3.3 | QA Standards | 1 | Sr. QA | 1 | 0.045455 | 2011-03-08 | 2011-03-08 | 487.5
2 | REQUIREMENTS | 102 | Sr. Business Analyst, Vendor | 2 | 4 | 2011-03-05 | 2011-07-05 | 34970
2.1 | REQUIREMENTS PACKAGE | 52 | Sr. Business Analyst | 1 | 2.3636 | 2011-03-05 | 2011-05-07 | 21970
2.2 | REQUIREMENTS ANALYSIS | 50 | Vendor | 1 | 2.2727 | 2011-05-05 | 2011-07-05 | - | 13000 | WP1
3 | DESIGN | 394 | Vendor, Data Modeler | 2 | 14 | 2011-07-07 | 2012-09-05 | 131931.6667
3.1 | SOLUTION DESIGN | 289 | Vendor, Data Modeler | 2 | 6.5682 | 2011-07-07 | 2012-09-05 | 78190
3.1.1 | TRAIS Data Model | 143 | Vendor, Data Modeler | 2 | 3.25 | 2011-07-07 | 2012-02-05 | -
3.1.1.1 | XML Schema | 25 | Vendor | 1 | 1.1364 | 2011-07-05 | 2011-08-05 | - | 24500 | WP1
3.1.1.2 | Physical Data Model (Relational) | 62.5 | Data Modeler | 1 | 2.8409 | 2011-08-05 | 2011-11-05 | 28437.5
3.1.1.3 | Physical Dimensional Data Model | 55.5 | Data Modeler | 1 | 2.5227 | 2011-11-05 | 2012-02-05 | 25252.5
3.1.2 | GHGIS Data Model | 146 | Vendor, Data Modeler | 2 | 7 | 2012-02-05 | 2012-09-05 | 80055
3.1.2.1 | XML Schema | 25 | Vendor | 1 | 1.1364 | 2012-02-05 | 2012-03-05 | - | 25000 | WP1
3.1.2.2 | Physical Data Model (Relational) | 60.5 | Data Modeler | 1 | 2.75 | 2012-03-05 | 2012-06-05 | 27527.5
3.1.2.3 | Physical Dimensional Data Model | 60.5 | Data Modeler | 1 | 2.75 | 2012-06-05 | 2012-09-05 | 27527.5
3.2 | DESIGN DOCUMENTATION | 50 | Vendor | 1 | 1 | 2011-07-07 | 2011-08-05 | 21000 |  | WP1
3.2.1 | TRAIS Documentation | 25 | Vendor | 1 | 1.1364 | 2011-07-05 | 2011-08-05 | - | 10500 | WP1
3.2.2 | GHGIS Documentation | 25 | Vendor | 1 | 1.1364 | 2011-07-05 | 2011-08-05 | - | 10500 | WP1
3.3 | COGNOS REPORTS DESIGN SPEC REVIEW | 55 | Vendor | 1 | 2.5 | 2011-08-05 | 2011-09-15 | 32741.6667
3.3.1 | TRAIS Reports Design Review | 30 | BA, QA, Vendor, BI | 4 | 0.34091 | 2011-08-05 | 2011-08-25 | 15870.8333 | 5200 | WP2
3.3.3.1 | Review of individual TRAIS Reports | 25 | Sr.BA, Sr. QA, Vendor | 3 | 0.37879 | 2011-08-05 | 2011-08-20 | 7583.3333
3.3.3.2 | Update and Acceptance of TRAIS Design Reports | 5 | BI | 1 | 0.22727 | 2011-08-20 | 2011-08-25 | 3087.5
3.3.2 | GHGIS Reports Design Review | 30 | Sr. BA, Sr. QA, Vendor, BI | 4 | 0.34091 | 2011-08-25 | 2011-09-15 | 16870.8333 | 6200 | WP2
3.3.2.1 | Review of individual TRAIS Reports | 25 | Sr.BA, Sr. QA, Vendor | 3 | 0.37879 | 2011-08-25 | 2011-09-10 | 7583.3333
3.3.3.2 | Update and Acceptance of GHGIS Design Reports | 5 | BI | 1 | 0.22727 | 2011-09-10 | 2011-09-15 | 3087.5
4 | INFRASTRUCTURE SETUP & IMPLEMENTATION | 135 | DBA, BI, QA | 3 | 2.0455 | 2011-08-05 | 2012-01-15 | 48587.5
4.1 | Build Test Environment | 45 | DBA, BI, QA | 3 | 0.68182 | 2011-08-05 | 2011-09-30 | 20637.5
4.1.1 | Create database in Test Environment | 20 | DBA | 1 | 0.90909 | 2011-08-05 | 2011-08-25 | 7150
4.1.2 | Setup & Config Cognos Environment | 10 | BI Specialist | 1 | 0.45455 | 2011-08-25 | 2011-09-15 | 6175
4.1.3 | Test setup of components (OWNERS, SSI, COGNOS) | 15 | Sr. QA | 1 | 0.68182 | 2011-09-15 | 2015-09-30 | 7312.5
4.2 | Build Staging Environment | 45 | DBA, BI, QA | 3 | 0.68182 | 2011-09-30 | 2011-11-15 | 20637.5
4.2.1 | Create database in Staging Environment | 20 | DBA | 1 | 0.90909 | 2011-09-30 | 2011-10-20 | 7150
4.2.2 | Setup & Config Cognos Environment | 10 | BI Specialist | 1 | 0.45455 | 2011-10-20 | 2011-10-30 | 6175
4.2.3 | Test setup of components (OWNERS, SSI, COGNOS) | 15 | Sr. QA | 1 | 0.68182 | 2011-11-01 | 2011-11-15 | 7312.5
4.3 | Build Production Environment | 45 | CCM Sr. QA | 2 | 1.0227 | 2011-11-15 | 2012-01-15 | 7312.5
4.3.1 | Create database in Prod Environment | 20 | Corp Chg Mgmt | 1 | 0.90909 | 2011-11-15 | 2011-12-10 | 0
4.3.2 | Setup & Config Cognos Environment | 10 | Cor Chg Mgmt | 1 | 0.45455 | 2011-12-10 | 2011-12-20 | 0
4.3.3 | Test setup of components (OWNERS, SSI, COGNOS) | 15 | Sr. QA | 1 | 0.68182 | 2012-01-01 | 2012-01-15 | 7312.5
5 | CONSTRUCTION | 292 |  | 1 | 13.2727 | 2011-08-05 | 2012-06-05 | 269200
5.1 | BUILD ETL SOLUTION | 132 | Vendor | 1 | 1 | 2011-08-05 | 2012-02-05 | - | 116400 | WP2/WP3
5.1.1 | ETL 1 TRAIS/GHGIS (to staging db) | 66 | Vendor | 1 | 3 | 2011-08-05 | 2011-11-05 | - | 64000 | WP2
5.1.2 | ETL 2 TRAIS/GHGIS (staging to data mart) | 66 | Vendor | 1 | 3 | 2011-11-06 | 2012-02-05 | - | 52400 | WP3
5.2 | COGNOS REPORT BUILD | 160 | Vendor | 1 | 7.2727 | 2012-02-05 | 2012-06-05 | - | 152800
5.2.1 | TRAIS Reports | 80 | Vendor | 1 | 3.6364 | 2012-02-05 | 2012-06-05 | - | 87100 | WP3
5.2.2 | GHGIS REPORTS | 80 | Vendor | 1 | 3.6364 | 2012-02-05 | 2012-06-05 | - | 65700 | WP3
6 | TEST | 208.5 | Vendor, QA, SA, SAM, BI | 5 | 10 | 2011-11-05 | 2012-08-05 | 99176.25
6.1 | SYSTEM TEST (Functional Testing) | 157.5 | Vendor, QA, SA, SAM, BI | 5 | 1.4318 | 2012-06-05 | 2012-06-30 | 75743.75
6.1.1 | Planning | 25 | Vendor | 1 | 1.1364 | 2012-06-05 | 2012-06-25 | - | 6500 | WP 2
6.1.2 | Test Data | 22.5 | QA, SA | 2 | 0.51136 | 2012-06-05 | 2012-06-28 | 10643.75
6.1.2.1 | Create/Acquire TRAIS test data | 10 | Sr. QA | 1 | 0.45455 | 2012-06-05 | 2012-06-15 | 4875
6.1.2.2 | Create/Acquire GHGIS test data | 10 | Sr. QA | 1 | 0.45455 | 2012-06-15 | 2012-06-25 | 4875
6.1.2.3 | Load data to test environment | 2 | SAM | 1 | 0.090909 | 2012-06-25 | 2012-06-28 | 715
6.1.2.4 | Establish Tester User Names/Pwrds | 0.5 | SAM | 1 | 0.022727 | 2012-06-25 | 2012-06-25 | 178.75
6.1.3 | Test Case/Test Script Documentation | 70 | Vendor | 1 | 3.1818 | 2011-08-05 | 2011-11-05 | - | 25000 | WP2/WP3
6.1.4 | System Test & Defect Resolution Cycle | 40 | BI, Vendor, QA | 3 | 0.60606 | 2011-11-05 | 2012-06-25 | 33600
6.1.4.1 | ETL 1 TRAIS/GHGIS (to staging db) | 20 | BI Specialist, Vendor | 2 | 0.45455 | 2011-11-05 | 2011-12-05 | 6175 | 5000 | WP2
6.1.4.2 | ETL 2 TRAIS/GHGIS (staging to data mart) | 20 | BI Specialist, Vendor | 2 | 0.45455 | 2012-02-05 | 2012-03-05 | 6175 | 6500 | WP3
6.1.4.3 | Cognos Reports TRAIS (incl defect cycle) | 10 | Sr.QA | 1 | 0.45455 | 2012-06-05 | 2012-06-25 | 4875
6.1.4.4 | Cognose Reports GHGIS (incl defect cycle) | 10 | Sr.QA | 1 | 0.45455 | 2012-06-05 | 2012-06-25 | 4875
6.2 | USER ACCEPTANCE TESTING (Staging Environment) | 51 | SAM, BI, DBA, BA | 4 | 0.57955 | 2011-11-05 | 2012-08-05 | 23432.5
6.2.1 | Load data to staging environment | 1 | SAM | 1 | 0.045455 | 2011-11-05 | 2011-11-05 | 357.5
6.2.2 | Test ETL (staging & Cognos) | 15 | BI Specialist | 1 | 0.68182 | 2012-02-05 | 2012-02-20 | 9262.5
6.2.3 | Batch Test Scripts | 15 | DBA | 1 | 0.68182 | 2011-11-15 | 2012-01-05 | 5362.5
6.2.4 | Cognos Reports TRAIS (incl defect cycle) | 10 | Sr. BA | 1 | 0.45455 | 2012-06-15 | 2012-07-15 | 4225
6.2.5 | Cognose Reports GHGIS (incl defect cycle) | 10 | Sr. BA | 1 | 0.45455 | 2012-06-25 | 2012-07-05 | 4225
6.2.6 | User Accepance | 30 | Bus Stakeholders | 1 | 1.3636 | 2012-07-05 | 2012-08-05 | 0
7 | IMPLEMENTATION | 4 | SAM, QA, CCM | 3 | 0.060606 | 2012-08-05 | 2012-08-30 | 4062.5
7.1 | Code Deployment | 11 | SAM ,QA, CCM | 3 | 0.16667 | 2012-08-05 | 2012-08-30 | 4062.5
7.1.1 | Submit corporate RFC to move code to Prod | 5 | SAM | 1 | 0.22727 | 2012-08-05 | 2012-08-10 | 1787.5
7.1.2 | Deploy Code to Prod Servers | 5 | SAM | 1 | 0.22727 | 2012-08-10 | 2012-08-15 | 1787.5
7.1.3 | Conduct Sanity Test | 1 | Sr. QA | 1 | 0.045455 | 2012-08-15 | 2012-08-15 | 487.5
7.1.4 | Go Live | 0 | Corp Chg Mgmt | 1 | 0 | 2012-08-30 | 2012-08-30 | 0
8 | TRANSITON TO OPERATIONS | 170 | Vendor, BI | 1 | 7.7273 | 2012-06-05 | 2012-11-20 | 113851
8.1 | Operations | 120 | Vendor, SD, SAM | 1 | 5.4545 | 2012-06-05 | 2012-09-20 | 83513 | 62000 | WP4
8.1.2 | ETL Run Book Review & Acceptance (TRAIS) | 5 | Sol Designer, SAM | 2 | 0.11364 | 2012-07-15 | 2012-07-20 | 1950
8.1.4 | ETL Run Book Review & Acceptance (GHGIS) | 5 | Sol Designer, SAM | 2 | 0.11364 | 2012-07-15 | 2012-07-20 | 1950
8.1.6 | ETL Scheuler Doc Review & Acceptance (TRAIS) | 5 | Sol Designer, SAM | 2 | 0.11364 | 2012-07-30 | 2012-08-30 | 1950
8.1.8 | ETL Scheduler Doc Review & Acceptance (GHGIS) | 5 | Sol Designer, SAM | 2 | 0.11364 | 2012-07-30 | 2012-08-30 | 1950
8.1.9 | Document TRAIS-GHGIS Cognos User Guide | 15 | BI | 1 | 0.68182 | 2012-06-05 | 2012-06-25 | 9262.5
8.1.10 | Cognos UG Review & Acceptance | 5 | Sr. BA | 1 | 0.22727 | 2012-06-25 | 2012-06-30 | 2112.5
8.1.12 | Knowledge Base Doc Review & Acceptance | 5 | Core Team | 5 | 0.045455 | 2012-09-15 | 2012-09-20 | 2338
8.2 | End User Groups | 50 | Vendor | 1 | 2.2727 | 2012-09-09 | 2012-11-10 | 30338 | 28000 | WP4
8.2.2 | Training Pckge Review & Acceptance | 5 | Core Team | 3 | 0.075758 | 2012-10-15 | 2012-10-20 | 2338
9 | PROJECT CLOSE-OUT | 40.8 |  | 1 | 1.8545 | 2012-11-10 | 2012-11-20 | 17026.75
9.1 | Administration | 30 | Project Manager | 1 | 1.3636 | 2012-11-10 | 2012-12-20 | 12675
9.2 | Lessons Learned | 10.3 | Project Manager | 1 | 0.46818 | 2012-11-10 | 2012-11-20 | 4351.75
Total Effort |  | 1452.3 |  |  |  | 2011-01-05 | 2012-11-20
Total Estimted Cost | [7 empty] | 761965.6667
Project Duration: 1 yr and 11 months
Rates
PM ($65/hr) - 422 daily rate
QA ($75/hr) - $487 daily rate
BI ($95/hr) – 617 daily rate
Sr. BA ($65/hr) - $422 daily rate
Data Modeler ($70/hr) – $455 daily rate
DBA ($55/hr) - $357 daily rate
SD or Dev ($65/hr) - $422 daily rate
Systems Analyst/Middleware - SAM ($55/hr) - $357 daily rate
Using 6.5 hrs/day and 22 working days/month

## Budget
|  | Q1 - 2011 | [8 empty] | Q2-2011 | [8 empty] | Q3-2011
| Rate (day) | January |  |  | February |  |  | March |  |  | April |  |  | May |  |  | June |  |  | July
Consultant Reources |  | Estimate | Project Costs | Var | Estimate | Project Costs | Var | Estimate | Project Costs | Var | Estimate | Project Costs | Var | Estimate | Project Costs | Var | Estimate | Project Costs | Var | Estimate | Project Costs | Var
Sr. Business Analyst | 422.5 | 9295 | 0 | 9295 | 9295 | 0 | 9295 | 9295 | 8027.5 | 1267.5 | 9295 | 9295 | 0 | 9295 | 2112.5 | 7182.5 | 9295 |  | 9295 | 9295 |  | 9295
Sr. Quality Assurance Analyst | 487.5 | 10725 | 0 | 10725 | 10725 | 0 | 10725 | 10725 | 487.5 | 10237.5 | 10725 | 0 | 10725 | 10725 | 0 | 10725 | 10725 |  | 10725 | 10725 |  | 10725
BI Consultant | 617 | 13574 | 0 | 13574 | 13574 | 0 | 13574 | 13574 | 0 | 13574 | 13574 | 0 | 13574 | 13574 | 0 | 13574 | 13574 |  | 13574 | 13574 |  | 13574
Fixed Price Vendor Team |  | Q1 - 2011 | [5 empty] | Q2 - 2011 | [5 empty] | Q3-2011
|  | January |  | February |  | March |  | April |  | May |  | June |  | July
| Cost | Spent | Var | Cost | Var | Spent | Var | Spent | Var | Spent | Var | Spent | Var | Spent | Var
Work Package 1 - Requirements Analysis & Documentation | 200000 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 13000 | 187000
Work Package 2 - ETL Inbound | 85000 | 0 | 85000 | 0 | 85000 | 0 | 85000 | 0 | 85000 | 0 | 85000 | 0 | 85000 | 0 | 85000
Work Pacakge 2 - ETL Reports | 295000 | 0 | 295000 | 0 | 295000 | 0 | 295000 | 0 | 295000 | 0 | 295000 | 0 | 295000 | 0 | 295000
Work Package 4 - System Documentation | 90000 | 0 | 90000 | 0 | 90000 | 0 | 90000 | 0 | 90000 | 0 | 90000 | 0 | 90000 | 0 | 90000

## Status Report
Project:Enterprise Reporting Solution | [9 empty] | Project Manager: [Kartik Sojitra] | [14 empty] | Report Date: 07/31/2011
Objective: Design, build, and implement an enterprise reporting solution for two data sets TRAIS and GHGIS
Sub-objectives | [6 empty] | Major Tasks |  |  | Schedule | [11 empty] | Owner
⚫ | [6 empty] | 1.1.1 | Integrated Project Plan |  |  | ⚫ | [15 empty] | P
⚫ | [6 empty] | 1.2.1 | Procurement - Vendor Team |  |  | ⚫ | [15 empty] | P
⚫ | [6 empty] | 1.2.2 | Procurement - Consultants |  |  |  | ⚫ | [14 empty] | P
⚫ | [6 empty] | 1.3 | Vendor Ramp up |  |  |  | ⚫ | [9 empty] | S |  |  | S |  | P
| ⚫ | [5 empty] | 2.1 | Requirements Package | [5 empty] | ⚫ | [9 empty] | P
| ⚫ | [5 empty] | 2.2 | Requirements Analysis | [7 empty] | ⚫ | [5 empty] | P
[7 empty] | 3.1.1 | Solution Design - TRAIS Data Model | [13 empty] | P |  |  |  | S
[7 empty] | 3.1.2 | Solution Design - GHGIS Data Model | [13 empty] | P |  |  |  | S
|  | ◯ |  |  |  |  | 3.2.1 | TRAIS Documentation | [7 empty] | ◯ | [5 empty] | P
|  | ◯ |  |  |  |  | 3.2.2 | GHGIS Documentation | [7 empty] | ◯ | [5 empty] | P
[7 empty] | 3.3.1 | TRAIS Design Report Review | [13 empty] | S | S | P | S
[7 empty] | 3.3.2 | GHGIS Design Report Review | [13 empty] | S | S | P | S
|  |  |  | ◯ |  |  | 4.1 | Build Test Environment | [14 empty] | S |  | S
|  |  |  | ◯ | ◯ |  | 4.2 | Build Staging Environment | [14 empty] | S |  | S
|  |  |  | ◯ | ◯ |  | 4.3 | Build Production Environment | [16 empty] | S
|  |  | ◯ |  |  |  | 5.1.1 | ETL 1 TRAIS/GHGIS | [13 empty] | P
|  |  | ◯ |  |  |  | 5.1.2 | ETL 2 TRAIS/GHGIS | [13 empty] | P
[6 empty] | ◯ | 5.2.1 | Build TRAIS Reports | [13 empty] | P
[6 empty] | ◯ | 5.2.2 | Build GHGIS Reports | [13 empty] | P
[7 empty] | 6.1 | System Test | [13 empty] | S | S |  | P
[7 empty] | 6.2 | User Acceptance Testing | [14 empty] | S | P
[7 empty] | 7.1 | Code Deployment | [16 empty] | S
|  | ◯ |  |  |  |  | 8.1 | Operations Documentation | [13 empty] | P
[7 empty] | 8.2 | End User Group Testing | [13 empty] | P
[7 empty] | 9.1 | Project Close Out Administration | [18 empty] | P
[7 empty] | 9.2 | Project Close Out Lessons Learned | [18 empty] | P
[7 empty] | Risk Tracking |  |  | green=adequate ¦ yellow=worrisome ¦ red=dangerous | [11 empty] | P=primary ¦ S=secondary
[7 empty] | 1 | Project deadline | [13 empty] | S |  |  |  |  | P
[7 empty] | 2 | Undertrained vendor team | [13 empty] | P
[7 empty] | 3 | Uncertain consultant contract | [18 empty] | P
[7 empty] | 4 | Varying prices of the project assets | [18 empty] | P
[7 empty] | 5 | Incorrect budget estimation | [18 empty] | P
[9 empty] | # People working on the project: | Months | [11 empty] | Resources
Planning | Requirements | Documentation | ETL Build | Databaase Builds | Cognos Setup | Cognos Reports | ⯅ Major Tasks and Risks |  | Report Dates ⯈ | January | February | March | April | May | June | July | August | September | October | November | December | Vendor | BI Specialist | Sr. BA | Sr. QA | Data Modeller | Project Manager
[7 empty] | ⯇ Sub-objectives |  | Costs and Metrics ⯈ | [12 empty] | Legend
[22 empty] | ◯ | work in progress
[22 empty] | ⚫ | work complete
[22 empty] | ◯ | work delayed
[22 empty] | ⯁ | milestone
Summary and Forecast ⯈ | [6 empty] | <Text description of status here: i.e. the why, the plan to recover>