## Task_Table
ID | Task Name | Resource (s) | Effort (days) | # Resource(s) | Duration (mon) | Anticipated Start | Anticipated End
1 | PLANNING |  | 106 |  | 4.3636
1.1 | PROJECT ADMINISTRATION |  | 20 |  | 0.90909
1.1.1 | Integrated Project Plan | Project Manager | 20 |  | 0.90909 | 2011-01-05 | 2011-02-05
1.1.1.1 | Draft project work plan (task list) | PM | 10 | 1 | 0.45455
1.1.1.2 | Draft project schedule | PM | 10 | 1 | 0.45455
1.1.1.3 | Distribute to TRAIS-GHGIS project team | PM | 0 | 1 | 0
1.2 | PROCUREMENT |  | 82 |  | 3.2727 | 2011-01-05 | 2011-03-05
1.2.1 | Development Team |  | 30 |  | 1.2955 | 2011-01-05 | 2011-02-05
1.2.1.1 | Draft Change Orders (CO) | PM | 5 | 1 | 0.22727
1.2.1.2 | Distribute CO's for review and feedback | PM, Mgrsx3 | 2 | 4 | 0.022727
1.2.1.3 | Negotiate with Vendor and obtain Work Plackage (WP) costs | PM | 5 | 1 | 0.22727
1.2.1.4 | Send Change Orders for Legal Review | PM | 5 | 1 | 0.22727
1.2.1.5 | Finalize CO's based on legal review | PM | 2 | 1 | 0.090909
1.2.1.6 | Obtain Signatures | PM | 10 | 1 | 0.45455
1.2.1.7 | Finalize deliverable acceptance sheet | PM | 1 | 1 | 0.045455
1.2.2 | Consultant: Business Analyst & BI Specialist |  | 48 |  | 1.9773 | 2011-01-05 | 2011-03-05
1.2.2.1 | Draft Request for Services (RFS) | PM | 5 | 1 | 0.22727
1.2.2.2 | Legal Review of RFS | Legal | 5 | 1 | 0.22727
1.2.2.3 | Finalize and Issue RFS | PM | 3 | 1 | 0.13636
1.2.2.4 | Receive proposals | PM | 1 | 1 | 0.045455
1.2.2.5 | Individual Evaluation | PM, Mgr x 3 | 5 | 4 | 0.056818
1.2.2.6 | Concensus meeting & Selection | PM, Mgrs x3 | 1 | 4 | 0.011364
1.2.2.7 | Draft SOW | PM | 5 | 1 | 0.22727
1.2.2.8 | Legal Review (SOW) | Legal | 5 | 1 | 0.22727
1.2.2.9 | Finalize (SOW) | PM | 3 | 1 | 0.13636
1.2.2.10 | Obtain Security Clearance for resources | PM | 10 | 1 | 0.45455
1.2.2.11 | Finalize and award SOW to vendor | PM | 5 | 1 | 0.22727
1.2.2.12 | Resource Start Date | N/a | 0 | 1 | 0
1.3 | VENDOR RAMP UP |  | 4 |  | 0.18182 | 2011-03-06 | 2011-03-10
1.3.1 | I&IT Standards Review Workshop(s) | PM | 2 | 1 | 0.090909
1.3.2 | I&IT Design & Build Standards Workshop | Dev | 1 | 1 | 0.045455
1.3.3 | QA Standards | Sr. QA | 1 | 1 | 0.045455
2 | REQUIREMENTS |  | 142 |  | 6.0649
2.1 | REQUIREMENTS PACKAGE |  | 52 |  | 2.3636 | 2011-03-11 | 2011-05-20
2.1.1 | Document Solution Requirements | Sr. BA | 20 | 1 | 0.90909
2.1.2 | Document TRAIS Report Requirements | Sr. BA | 15 | 1 | 0.68182
2.1.3 | Document GHGIS Report Requirements | Sr. BA | 15 | 1 | 0.68182
2.1.4 | System Use Case Package (Provide to Vendor) | Sr. BA | 1 | 1 | 0.045455
2.1.5 | Report Specification Package (Provide to Vendor) | Sr. BA | 1 | 1 | 0.045455
2.2 | REQUIREMENTS ANALYSIS |  | 90 |  | 3.7013 | 2011-05-21 | 2011-09-08
2.2.1 | Physical Data Model |  | 40 |  | 1.8182 | 2011-05-21 | 2011-07-14
2.2.2.1 | Physical Data Model Analysis (TRAIS) | DM | 20 | 1 | 0.90909
2.2.2.2 | Physical Data Model Analysis (GHGIS) | DM | 20 | 1 | 0.90909
2.2.3 | Dimension Model |  | 40 |  | 1.8182 | 2011-07-15 | 2011-09-06
2.2.3.1 | Physical Dimension Model Analysis (TRAIS) | DM | 25 | 1 | 1.1364
2.2.3.2 | Physical Dimension Model Analysis (GHGIS) | DM | 15 | 1 | 0.68182
2.2.4 | Review of Requirements Package |  | 10 |  | 0.064935 | 2011-09-07 | 2011-09-08
2.2.4.1 | TRAIS Requirements Review Sessions | DM, Sr. BA, Sr. QA, DBA, Vendor, Dev,BI | 5 | 7 | 0.032468
2.2.4.2 | GHGIS Requirements Review Sessons | DM, Sr. BA, Sr. QA, DBA, Vendor, Dev, BI | 5 | 7 | 0.032468
3 | DESIGN |  | 394 |  | 14.6656
3.1 | SOLUTION DESIGN |  | 289 |  | 11.3052 | 2011-09-09 | 2012-08-12
3.1.1 | TRAIS Data Model |  | 143 |  | 5.6818 | 2011-09-09 | 2012-02-25
3.1.1.1 | XML Schema |  | 25 |  | 0.94156 | 2011-09-09 | 2011-10-06
3.1.1.1.1 | Draft XML Schema | DM | 15 | 1 | 0.68182
3.1.1.1.2 | XML walkthrough and feedback | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 5 | 7 | 0.032468
3.1.1.1.3 | XML finalized and redistribute | DM | 5 | 1 | 0.22727
3.1.1.1.4 | XML Acceptance | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 0 | 1 | 0
3.1.1.2 | Physical Data Model (Relational) |  | 62.5 |  | 2.4318 | 2011-10-06 | 2011-12-17
3.1.1.2.1 | Draft Physical Data Model | DM | 25 | 1 | 1.1364
3.1.1.2.2 | Distribute draft, review, and feedback | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 10 | 7 | 0.064935
3.1.1.2.3 | Generate DDL's and provide to Vendor | DM | 5 | 1 | 0.22727
3.1.1.2.4 | Data Model Walkthrough | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 0.5 | 7 | 0.0032468
3.1.1.2.5 | Add tables for notification | DBA | 2 | 1 | 0.090909
3.1.1.2.6 | Add metadata to all tables | DBA | 5 | 1 | 0.22727
3.1.1.2.7 | Map LDM to PDM | DM | 15 | 1 | 0.68182
3.1.1.2.8 | Acceptance of PDM | DBA, BI, Dev, Vendor | 0 | 1 | 0
3.1.1.3 | Physical Dimensional Data Model |  | 55.5 |  | 2.3084 | 2011-12-18 | 2012-02-25
3.1.1.3.1 | Draft Physical Data Model | DM | 30 | 1 | 1.3636
3.1.1.3.2 | Distribute draft, review, and feedback | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 5 | 7 | 0.032468
3.1.1.3.3 | Generate DDL's and provide to Vendor | DM | 5 | 1 | 0.22727
3.1.1.3.4 | Data Model Walkthrough | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 0.5 | 7 | 0.0032468
3.1.1.3.5 | Add metadata to all tables | DBA | 5 | 1 | 0.22727
3.1.1.3.6 | Map Logical Data Model (LDM) to Physical Data Model (PDM) | DM | 10 | 1 | 0.45455
3.1.1.3.7 | Acceptance of PDDM | DBA, BI, Dev, Vendor | 0 | 1 | 0
3.1.2 | GHGIS Data Model |  | 146 |  | 5.6234 | 2012-02-26 | 2012-08-12
3.1.2.1 | XML Schema |  | 25 |  | 0.94156 | 2012-02-26 | 2012-03-25
3.1.2.1.1 | Draft XML Schema | DM | 15 | 1 | 0.68182
3.1.2.1.2 | XML walkthrough and feedback | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 5 | 7 | 0.032468
3.1.2.1.3 | XML finalized and redistribute | DM | 5 | 1 | 0.22727
3.1.2.1.4 | XML Acceptance | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 0 | 1 | 0
3.1.2.2 | Physical Data Model (Relational) |  | 60.5 |  | 2.3409 | 2012-03-26 | 2012-06-03
3.1.2.2.1 | Draft Physical Data Model | DM | 25 | 1 | 1.1364
3.1.2.2.2 | Distribute draft, review, and feedback | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 10 | 7 | 0.064935
3.1.2.2.3 | Generate DDL's and provide to Vendor | DM | 5 | 1 | 0.22727
3.1.2.2.4 | Data Model Walkthrough | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 0.5 | 7 | 0.0032468
3.1.2.2.5 | Add tables for notification | DBA | 5 | 1 | 0.22727
3.1.2.2.6 | Add metadata to all tables | DBA | 5 | 1 | 0.22727
3.1.2.2.7 | Map LDM to PDM | DM | 10 | 1 | 0.45455
3.1.2.2.8 | Acceptance of PDM | DBA, BI, Dev, Vendor | 0 | 1 | 0
3.1.2.3 | Physical Dimensional Data Model |  | 60.5 |  | 2.3409 | 2012-06-04 | 2012-08-12
3.1.2.3.1 | Draft Physical Data Model | DM | 30 | 1 | 1.3636
3.1.2.3.2 | Distribute draft, review, and feedback | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 10 | 7 | 0.064935
3.1.2.3.3 | Generate DDL's and provide to Vendor | DM | 5 | 1 | 0.22727
3.1.2.3.4 | Data Model Walkthrough | Dev, Sr. BA, Sr. QA, DBA, Vendor, BI | 0.5 | 7 | 0.0032468
3.1.2.3.5 | Add metadata to all tables | DBA | 5 | 1 | 0.22727
3.1.2.3.6 | Map Logical Data Model (LDM) to Physical Data Model (PDM) | DM | 10 | 1 | 0.45455
3.1.2.3.7 | Acceptance of PDDM | DBA, BI, Dev, Vendor | 0 | 1 | 0
3.2 | DESIGN DOCUMENTATION |  | 50 |  | 1.8831 | 2012-08-13 | 2012-10-07
3.2.1 | TRAIS Documentation |  | 25 |  | 0.94156 | 2012-08-13 | 2012-09-09
3.2.1.1 | Initial Draft (TRAIS) | Vendor | 20 | 1 | 0.90909
3.2.1.2 | Review, Feedback, Finalize (TRAIS) | Core Team, Vendor | 5 | 7 | 0.032468
3.2.1.3 | TRAIS Acceptance | Core Team | 0 | 1 | 0
3.2.2 | Documentation (GHGIS) |  | 25 |  | 0.94156 | 2012-08-13 | 2012-09-09
3.2.2.1 | Initial Draft (GHGIS) | Vendor | 20 | 1 | 0.90909
3.2.2.2 | Review, Feedback, Finalize (GHGIS) | Core Team, Vendor | 5 | 7 | 0.032468
3.2.2.3 | GHGIS Acceptance | Core Team | 0 | 1 | 0
3.3 | COGNOS REPORTS DESIGN SPEC REVIEW |  | 55 |  | 1.4773 | 2012-09-10 | 2012-10-23
3.3.1 | TRAIS Reports Design Review |  | 30 |  | 0.79545 | 2012-09-10 | 2012-10-03
3.3.3.1 | Review of individual TRAIS Reports | Sr. BA, Sr. QA | 25 | 2 | 0.56818
3.3.3.2 | Update and Acceptance of TRAIS Design Reports | BI | 5 | 1 | 0.22727
3.3.2 | GHGIS Reports Design Review |  | 25 |  | 0.68182 | 2012-10-04 | 2012-10-23
3.3.2.1 | Review of individual TRAIS Reports | Sr. BA, Sr. QA | 20 | 2 | 0.45455
3.3.3.2 | Update and Acceptance of GHGIS Design Reports | BI | 5 | 1 | 0.22727
4 | INFRASTRUCTURE SETUP & IMPLEMENTATION |  | 135 |  | 5.7955 | 2012-10-24 | 2013-04-24
4.1 | Build Test Environment |  | 45 |  | 2.0455 | 2012-10-24 | 2012-12-25
4.1.1 | Create database in Test Environment | DBA | 20 | 1 | 0.90909
4.1.2 | Setup & Config Cognos Environment | BI | 10 | 1 | 0.45455
4.1.3 | Test setup of components (SWIM, SSI, COGNOS) | Sr. QA | 15 | 1 | 0.68182
4.2 | Build Staging Environment |  | 45 |  | 1.7045 | 2012-12-26 | 2013-02-14
4.2.1 | Create database in Staging Environment | DBA | 20 | 1 | 0.90909
4.2.2 | Setup & Config Cognos Environment | BI | 10 | 1 | 0.45455
4.2.3 | Test setup of components (SWIM, SSI, COGNOS) | Sr. QA, BI | 15 | 2 | 0.34091
4.3 | Build Production Environment |  | 45 |  | 2.0455 | 2013-02-15 | 2013-04-24
4.3.1 | Create database in Prod Environment | Operations | 20 | 1 | 0.90909
4.3.2 | Setup & Config Cognos Environment | Operations | 10 | 1 | 0.45455
4.3.3 | Test setup of components (SWIM, SSI, COGNOS) | Sr. QA | 15 | 1 | 0.68182
5 | CONSTRUCTION |  | 292 |  | 11.1439
5.1 | BUILD ETL SOLUTION |  | 132 |  | 5.6894 | 2013-04-25 | 2013-10-12
5.1.1 | ETL 1 TRAIS/GHGIS (to staging db) |  | 66 |  | 2.8258 | 2013-04-25 | 2013-07-18
5.1.1.1 | Build/Test ETL1 | Vendor | 40 | 1 | 1.8182
5.1.1.2 | Demo ETL1 Build | Vendor, Dev | 1 | 2 | 0.022727
5.1.1.3 | Finalize & Package ETL1 | Vendor | 5 | 1 | 0.22727
5.1.1.4 | Database script review | DBA | 5 | 1 | 0.22727
5.1.1.5 | Data Model Review | DM | 5 | 1 | 0.22727
5.1.1.6 | Deployment Guide Review | Sr. QA, DBA, DM | 5 | 3 | 0.075758
5.1.1.7 | Finalize &Package ETL1 | Vendor | 5 | 1 | 0.22727
5.1.2 | ETL 2 TRAIS/GHGIS (staging to data mart) |  | 66 |  | 2.8636 | 2013-04-25 | 2013-07-19
5.1.2.1 | Build/Test ETL2 | Vendor | 40 | 1 | 1.8182
5.1.2.2 | Demo ETL2 Build | Vendor, Dev | 1 | 2 | 0.022727
5.1.2.3 | Finalize & Package ETL2 | Vendor | 5 | 1 | 0.22727
5.1.2.4 | Database script review | DBA | 5 | 1 | 0.22727
5.1.2.5 | Data Model Review | DM | 5 | 1 | 0.22727
5.1.2.6 | Deployment Guide Review | Dev, SA | 5 | 2 | 0.11364
5.1.2.7 | Finalize &Package ETL2 | Vendor | 5 | 1 | 0.22727
5.2 | COGNOS REPORT BUILD |  | 160 |  | 5.4545 | 2013-07-20 | 2013-12-30
5.2.1 | TRAIS Reports |  | 80 |  | 2.7273 | 2013-07-20 | 2013-10-09
5.2.1.1 | TRAIS Reports Design Review | Sr. BA, Sr. QA | 5 | 2 | 0.11364
5.2.1.2 | Construct Data Mart | BI | 15 | 1 | 0.68182
5.2.1.3 | Construct User Interface | BI | 15 | 1 | 0.68182
5.2.1.4 | Build/Test Reports | BI, Sr. QA | 35 | 2 | 0.79545
5.2.1.5 | Update, Package, and Implement Reports | BI | 10 | 1 | 0.45455
| Accept TRAIS Reports | Business | 0 | 1 | 0
5.2.2 | GHGIS REPORTS |  | 80 |  | 2.7273 | 2013-10-10 | 2013-12-30
5.2.2.1 | GHGIS Reports Design Review | Sr. BA, Sr. QA | 5 | 2 | 0.11364
5.2.2.2 | Construct Data Mart | BI | 15 | 1 | 0.68182
5.2.2.3 | Construct User Interface | BI | 15 | 1 | 0.68182
5.2.2.4 | Build/Test Reports | BI, Sr. QA | 35 | 2 | 0.79545
5.2.2.5 | Update, Package, and Implement Reports | BI | 10 | 1 | 0.45455
| Accept GHGIS Reports | Business | 0 | 1 | 0
6 | TEST |  | 208.5 |  | 7.6212
6.1 | SYSTEM TEST (Functional Testing) |  | 157.5 |  | 5.9091 | 2013-12-31 | 2014-06-25
6.1.1 | Planning |  | 25 |  | 0.94697 | 2013-12-31 | 2014-01-28
6.1.1.1 | Draft Test Strategy | Sr. QA | 10 | 1 | 0.45455
6.1.1.2 | Document Test data requirements | Sr. QA | 10 | 1 | 0.45455
6.1.1.3 | Strategy review, feedback, update, finalize | Sr. BA, Vendor, Dev, DBA, DM, BI | 5 | 6 | 0.037879
6.1.1.4 | Test Strategy Acceptance | Sr. BA, Vendor, Dev, DBA, DM, BI | 0 | 1 | 0
6.1.2 | Test Data |  | 22.5 |  | 1.0227 | 2014-01-29 | 2014-02-28
6.1.2.1 | Create/Acquire TRAIS test data | Sr. QA | 10 | 1 | 0.45455
6.1.2.2 | Create/Acquire GHGIS test data | Sr. QA | 10 | 1 | 0.45455
6.1.2.3 | Load data to test environment | DBA | 2 | 1 | 0.090909
6.1.2.4 | Establish Tester User Names/Pwrds | SA | 0.5 | 1 | 0.022727
6.1.3 | Test Case/Test Script Documentation |  | 70 |  | 3.1818 | 2014-03-01 | 2014-06-03
6.1.3.1 | Draft Test Cases ETL 1 (incl. review & acceptance) | Sr. QA | 20 | 1 | 0.90909
6.1.3.2 | Draft Test Cases ETL 2 (incl. review & acceptance) | Sr. QA | 20 | 1 | 0.90909
6.1.3.3 | Draft Test Cases Cognos Reports (incl. review & acceptance) | Sr.QA | 30 | 1 | 1.3636
6.1.4 | System Test & Defect Resolution Cycle |  | 40 |  | 0.75758 | 2014-06-04 | 2014-06-25
6.1.4.1 | ETL 1 TRAIS/GHGIS (to staging db) | Sr. QA, Dev, DBA, Sr. BA | 20 | 4 | 0.22727
6.1.4.2 | ETL 2 TRAIS/GHGIS (staging to data mart) | Sr. QA, Dev, DBA, Sr. BA | 20 | 4 | 0.22727
6.1.4.3 | Cognos Reports TRAIS (incl defect cycle) | Sr. QA, BI, Sr. BA | 10 | 3 | 0.15152
6.1.4.4 | Cognose Reports GHGIS (incl defect cycle) | Sr. QA, BI, Sr. BA | 10 | 3 | 0.15152
6.2 | USER ACCEPTANCE TESTING (Staging Environment) |  | 51 |  | 1.7121 | 2014-06-26 | 2014-08-14
6.2.1 | Load data to staging environment | DBA | 1 | 1 | 0.045455
6.2.2 | Test ETL (staging & Cognos) | Sr. QA | 15 | 1 | 0.68182
6.2.3 | Batch Test Scripts | Sr. QA | 15 | 1 | 0.68182
6.2.4 | Cognos Reports TRAIS (incl defect cycle) | Sr. QA, BI, Sr. BA | 10 | 3 | 0.15152
6.2.5 | Cognose Reports GHGIS (incl defect cycle) | Sr. QA, BI, Sr. BA | 10 | 3 | 0.15152
6.2.6 | User Acceptance |  | 0 | 1 | 0
7 | IMPLEMENTATION |  | 4 |  | 0.18182
7.1 | Code Deployment |  | 4 |  | 0.18182 | 2014-08-15 | 2014-08-20
7.1.1 | Submit corporate RFC to move code to Prod | PM | 1 | 1 | 0.045455
7.1.2 | Deploy Code to Prod Servers | Operations | 2 | 1 | 0.090909
7.1.3 | Conduct Sanity Test | Sr. QA | 1 | 1 | 0.045455
7.1.4 | Go Live | N/A | 0 | 1 | 0
8 | TRANSITON TO OPERATIONS |  | 170 |  | 6.8939
8.1 | Operations |  | 120 |  | 4.8106 | 2014-08-21 | 2015-01-11
8.1.1 | Document ETL Run Book (TRAIS) | Vendor | 15 | 1 | 0.68182
8.1.2 | Review & Acceptance | Dev, SA | 5 | 2 | 0.11364
8.1.3 | Document ETL Run Book (GHGIS) | Vendor | 15 | 1 | 0.68182
8.1.4 | Review & Acceptance | Dev, SA | 5 | 2 | 0.11364
8.1.5 | Document ETL Scheduler System Document - TRAIS | Vendor | 15 | 1 | 0.68182
8.1.6 | Review & Acceptance | Dev, SA | 5 | 2 | 0.11364
8.1.7 | Document ETL Scheduler System Document - GHGIS | Vendor | 15 | 1 | 0.68182
8.1.8 | Review & Acceptance | Dev, SA | 5 | 2 | 0.11364
8.1.9 | Document TRAIS-GHGIS Cognos User Guide | BI | 15 | 1 | 0.68182
8.1.10 | Review & Acceptance | Sr. BA | 5 | 1 | 0.22727
8.1.11 | Knowledge Base Document | Vendor | 15 | 1 | 0.68182
8.1.12 | Finalize & Acceptance | Core Team | 5 | 6 | 0.037879
8.2 | End User Groups |  | 50 |  | 2.0833 | 2015-01-12 | 2015-03-14
8.2.1 | Develop Training Package (TRAIS & GHGIS) | Vendor | 25 | 1 | 1.1364
8.2.2 | Review & Acceptance | Core Team | 5 | 6 | 0.037879
8.2.3 | Conduct Knowledge Transfer Sessions | Vendor | 10 | 1 | 0.45455
8.2.4 | Conduct User Training Sessions | Vendor | 10 | 1 | 0.45455
9 | PROJECT CLOSE-OUT |  | 40.8 |  | 1.7539
9.1 | Administration |  | 30 |  | 1.3636 | 2015-03-15 | 2015-04-15
9.1.1 | Accept All Project Deliverables | PM | 5 | 1 | 0.22727
9.1.2 | Balance Project Budget | PM | 10 | 1 | 0.45455
9.1.3 | Closeout Contracts | PM | 15 | 1 | 0.68182
9.2 | Lessons Learned |  | 10.3 |  | 0.39026 | 2015-04-15 | 2015-04-27
9.2.1 | Schedule lessons learned (LL)session | PM | 0.5 | 1 | 0.022727
9.2.2 | Draft and Send out LL survey | PM | 2 | 1 | 0.090909
9.2.3 | Conduct LL Session | PM | 0.5 | 1 | 0.022727
9.2.4 | Draft LL Report | PM | 5 | 1 | 0.22727
9.2.5 | LL Report feedback, review, and finalize | Core Team, Vendor | 2 | 7 | 0.012987
9.2.6 | Distribute LL Report and Store in Project Repository | PM | 0.3 | 1 | 0.013636
9.3 | Team Celebration |  | 0.5 | 1 | 0.022727
Total Effort |  |  | 1492.3